## Slide 1
Construction Schedule
Free Gantt chart template · gantts.app

## Slide 2
Construction Schedule
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Pre-construction
Permits & approvals
Site survey
Foundation
Excavation
Pour foundation
Structure
Framing
Roofing
Interior
Electrical & plumbing
Finishing
◆ Handover
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Pre-construction |  | 2026-08-02 | 2026-08-21 | 20 | 100%
1.1 | Permits & approvals | PM | 2026-08-02 | 2026-08-13 | 12 | 100%
1.2 | Site survey | Surveyor | 2026-08-10 | 2026-08-15 | 6 | 100%
2 | Foundation |  | 2026-08-22 | 2026-09-05 | 15 | 30%
2.1 | Excavation | Crew A | 2026-08-22 | 2026-08-27 | 6 | 60%
2.2 | Pour foundation | Crew A | 2026-08-28 | 2026-09-05 | 9 | 0%
3 | Structure |  | 2026-09-06 | 2026-10-05 | 30 | 0%
3.1 | Framing | Crew B | 2026-09-06 | 2026-09-19 | 14 | 0%
3.2 | Roofing | Crew B | 2026-09-20 | 2026-09-29 | 10 | 0%
4 | Interior |  | 2026-10-06 | 2026-10-30 | 25 | 0%
4.1 | Electrical & plumbing | Trades | 2026-10-06 | 2026-10-17 | 12 | 0%
4.2 | Finishing | Trades | 2026-10-18 | 2026-10-30 | 13 | 0%
5 | Handover |  | 2026-10-31 | 2026-10-31 | — | —