## Gantt
Dissertation Timeline
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19
1 | Topic & proposal |  | 2026-08-02 | 2026-09-20 | 50
1.1 | Topic selection & reading | Student | 2026-08-02 | 2026-08-26 | 25
1.2 | Research questions & design | Student | 2026-08-22 | 2026-09-10 | 20
1.3 | Proposal written & submitted | Student | 2026-09-09 | 2026-09-20 | 12
2 | ◆ Proposal approved |  | 2026-09-21 | 2026-09-21 | [8 empty] | ◆
3 | Literature review |  | 2026-08-27 | 2026-11-24 | 90
3.1 | Systematic search & reading | Student | 2026-08-27 | 2026-10-15 | 50
3.2 | Synthesis & review chapter | Student | 2026-10-11 | 2026-11-24 | 45
4 | Methodology & ethics |  | 2026-09-21 | 2026-11-14 | 55
4.1 | Method & instrument design | Student | 2026-09-21 | 2026-10-20 | 30
4.2 | Ethics submission & review | Committee | 2026-10-16 | 2026-11-14 | 30
5 | ◆ Ethics approval |  | 2026-11-15 | 2026-11-15 | [16 empty] | ◆
6 | Data collection |  | 2026-11-15 | 2027-02-12 | 90
6.1 | Recruitment | Student | 2026-11-15 | 2026-12-14 | 30
6.2 | Fieldwork / data gathering | Student | 2026-12-05 | 2027-02-12 | 70
7 | Analysis |  | 2027-02-08 | 2027-04-08 | 60
7.1 | Data cleaning & coding | Student | 2027-02-08 | 2027-03-04 | 25
7.2 | Analysis & results write-up | Student | 2027-03-02 | 2027-04-08 | 38
8 | Drafting & submission |  | 2027-03-30 | 2027-07-12 | 105
8.1 | Full draft to supervisor | Student | 2027-03-30 | 2027-05-08 | 40
8.2 | Supervisor feedback | Supervisor | 2027-05-09 | 2027-05-28 | 20
8.3 | Revisions & formatting | Student | 2027-05-29 | 2027-07-02 | 35
9 | ◆ Submitted |  | 2027-07-13 | 2027-07-13 | [50 empty] | ◆