## Gantt
Hotel Pre-Opening Critical Path
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18
1 | Project set-up |  | 2026-08-02 | 2026-08-21 | 20
1.1 | Critical path & budget approved | GM | 2026-08-02 | 2026-08-13 | 12
2 | ◆ Opening date locked |  | 2026-08-22 | 2026-08-22 |  |  |  | ◆
3 | Recruitment & HR |  | 2026-08-22 | 2026-11-29 | 100
3.1 | Executive committee hired | HR | 2026-08-22 | 2026-09-20 | 30
3.2 | Department heads hired | HR | 2026-09-21 | 2026-10-25 | 35
3.3 | Line staff hiring wave | HR | 2026-10-26 | 2026-11-29 | 35
4 | OS&E and FF&E procurement |  | 2026-08-27 | 2026-11-29 | 95
4.1 | Specify & order OS&E | Purchasing | 2026-08-27 | 2026-10-10 | 45
4.2 | Delivery & storeroom set-up | Purchasing | 2026-10-31 | 2026-11-29 | 30
5 | Systems & IT |  | 2026-09-26 | 2026-11-29 | 65
5.1 | PMS & POS install | IT | 2026-09-26 | 2026-10-25 | 30
5.2 | Connectivity & integration test | IT | 2026-10-31 | 2026-11-29 | 30
6 | Sales & distribution |  | 2026-09-01 | 2026-12-09 | 100
6.1 | Rates, channels & OTA set-up | Commercial | 2026-09-01 | 2026-10-15 | 45
7 | ◆ Bookings open |  | 2026-10-16 | 2026-10-16 | [11 empty] | ◆
7.1 | Pre-opening sales push | Commercial | 2026-10-16 | 2026-12-09 | 55
8 | Licensing & inspections |  | 2026-11-10 | 2026-12-19 | 40
8.1 | Fire, health & liquor licences | Engineering | 2026-11-10 | 2026-12-04 | 25
9 | ◆ Certificate of occupancy |  | 2026-12-20 | 2026-12-20 | [21 empty] | ◆
10 | Training & opening |  | 2026-11-30 | 2027-01-13 | 45
10.1 | Departmental training | Dept heads | 2026-11-30 | 2026-12-24 | 25
10.2 | Soft opening | GM | 2026-12-30 | 2027-01-10 | 12
11 | ◆ Hotel open |  | 2027-01-14 | 2027-01-14 | [24 empty] | ◆