## Slide 1
Marketing Campaign Plan
Free Gantt chart template · gantts.app

## Slide 2
Marketing Campaign Plan
Aug 3
Aug 17
Aug 31
Strategy
Market research
Campaign brief
Content Production
Copywriting
Design assets
Video production
◆ Assets ready
Launch
Schedule posts
Go live & promote
Measure & optimize
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Strategy |  | 2026-08-02 | 2026-08-08 | 7 | 100%
1.1 | Market research | Analyst | 2026-08-02 | 2026-08-05 | 4 | 100%
1.2 | Campaign brief | CMO | 2026-08-06 | 2026-08-08 | 3 | 90%
2 | Content Production |  | 2026-08-09 | 2026-08-22 | 14 | 30%
2.1 | Copywriting | Writer | 2026-08-09 | 2026-08-14 | 6 | 50%
2.2 | Design assets | Designer | 2026-08-11 | 2026-08-18 | 8 | 25%
2.3 | Video production | Studio | 2026-08-13 | 2026-08-22 | 10 | 10%
3 | Assets ready |  | 2026-08-23 | 2026-08-23 | — | —
4 | Launch |  | 2026-08-23 | 2026-09-01 | 10 | 0%
4.1 | Schedule posts | Social | 2026-08-23 | 2026-08-25 | 3 | 0%
4.2 | Go live & promote | Team | 2026-08-26 | 2026-08-30 | 5 | 0%
4.3 | Measure & optimize | Analyst | 2026-08-31 | 2026-09-06 | 7 | 0%