## Slide 1
Solar Farm Construction Schedule
Free Gantt chart template · gantts.app

## Slide 2
Solar Farm Construction Schedule
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
Development & feasibility
Site control & pre-feasibility
Solar resource & layout
Interconnection & environmental
Interconnection application & study
Environmental assessment
◆ Interconnection agreement
Design & permitting
Civil & electrical design
Local permits & approvals
◆ Notice to proceed
Procurement
Modules & inverters ordered
Transformer & HV gear (long lead)
Civil & mechanical
Mobilization & access roads
Grading & fencing
Pile driving & racking
Module install & DC wiring
Electrical & commissioning
Inverters, combiners & substation
Testing & utility witness test
◆ Commercial operation
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Development & feasibility |  | 2026-08-02 | 2026-09-15 | 45 | 100%
1.1 | Site control & pre-feasibility | Development | 2026-08-02 | 2026-08-26 | 25 | 100%
1.2 | Solar resource & layout | Engineering | 2026-08-22 | 2026-09-15 | 25 | 100%
2 | Interconnection & environmental |  | 2026-09-11 | 2026-12-09 | 90 | 60%
2.1 | Interconnection application & study | Development | 2026-09-11 | 2026-11-24 | 75 | 70%
2.2 | Environmental assessment | Consultant | 2026-09-26 | 2026-11-14 | 50 | 60%
3 | Interconnection agreement |  | 2026-12-10 | 2026-12-10 | — | —
4 | Design & permitting |  | 2026-11-20 | 2027-01-18 | 60 | 30%
4.1 | Civil & electrical design | Engineering | 2026-11-20 | 2026-12-29 | 40 | 45%
4.2 | Local permits & approvals | Permitting | 2026-12-10 | 2027-01-18 | 40 | 20%
5 | Notice to proceed |  | 2027-01-19 | 2027-01-19 | — | —
6 | Procurement |  | 2026-12-20 | 2027-03-04 | 75 | 20%
6.1 | Modules & inverters ordered | Procurement | 2026-12-20 | 2027-02-17 | 60 | 30%
6.2 | Transformer & HV gear (long lead) | Procurement | 2026-12-20 | 2027-03-04 | 75 | 20%
7 | Civil & mechanical |  | 2027-01-21 | 2027-04-05 | 75 | 0%
7.1 | Mobilization & access roads | EPC | 2027-01-21 | 2027-02-04 | 15 | 0%
7.2 | Grading & fencing | Civil | 2027-02-03 | 2027-02-22 | 20 | 0%
7.3 | Pile driving & racking | Mechanical | 2027-02-20 | 2027-03-21 | 30 | 0%
7.4 | Module install & DC wiring | Mechanical | 2027-03-15 | 2027-04-05 | 22 | 0%
8 | Electrical & commissioning |  | 2027-03-30 | 2027-05-13 | 45 | 0%
8.1 | Inverters, combiners & substation | Electrical | 2027-03-30 | 2027-04-23 | 25 | 0%

## Slide 4
8.2 | Testing & utility witness test | Commissioning | 2027-04-22 | 2027-05-05 | 14 | 0%
9 | Commercial operation |  | 2027-05-14 | 2027-05-14 | — | —