## Gantt
Apparel Production Calendar
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15
1 | Concept & design |  | 2026-08-02 | 2026-08-31 | 30
1.1 | Range plan & design freeze | Design | 2026-08-02 | 2026-08-19 | 18
2 | ◆ Tech pack issued |  | 2026-09-01 | 2026-09-01 | [5 empty] | ◆
3 | Sampling |  | 2026-09-01 | 2026-11-14 | 75
3.1 | Proto sample | Sampling | 2026-09-01 | 2026-09-22 | 22
3.2 | Fit sample & comments | Sampling | 2026-09-23 | 2026-10-17 | 25
3.3 | PP sample | Sampling | 2026-10-18 | 2026-11-14 | 28
4 | ◆ PP sample approved |  | 2026-11-15 | 2026-11-15 | [16 empty] | ◆
5 | Materials |  | 2026-09-06 | 2026-11-24 | 80
5.1 | Fabric booking & lab dips | Sourcing | 2026-09-06 | 2026-10-10 | 35
5.2 | Bulk fabric production & transit | Mill | 2026-10-11 | 2026-11-24 | 45
6 | ◆ Fabric in-house |  | 2026-11-25 | 2026-11-25 | [17 empty] | ◆
7 | Pre-production |  | 2026-11-15 | 2026-12-06 | 22
7.1 | Marker, grading & size set | Production | 2026-11-15 | 2026-11-29 | 15
7.2 | PP meeting & line release | Production | 2026-11-30 | 2026-12-06 | 7
8 | Bulk production |  | 2026-12-07 | 2027-01-20 | 45
8.1 | Cutting | Factory | 2026-12-07 | 2026-12-16 | 10
8.2 | Sewing & in-line QC | Factory | 2026-12-17 | 2027-01-13 | 28
8.3 | Finishing & pressing | Factory | 2027-01-09 | 2027-01-20 | 12
9 | Finishing & shipment |  | 2027-01-21 | 2027-02-14 | 25
9.1 | Final inspection & packing | QA | 2027-01-21 | 2027-01-30 | 10
10 | ◆ Ex-factory |  | 2027-02-03 | 2027-02-03 | [27 empty] | ◆
10.1 | Transit to delivery window | Logistics | 2027-02-03 | 2027-02-14 | 12