## Slide 1
Employee Onboarding Plan
Free Gantt chart template · gantts.app

## Slide 2
Employee Onboarding Plan
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Pre-boarding
Offer, contract & IT setup
Day 1
Orientation & workspace
Week 1
Training & intro meetings
First 90 days
Role ramp & check-ins
◆ 90-day review
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Pre-boarding |  | 2026-08-02 | 2026-08-06 | 5 | 100%
1.1 | Offer, contract & IT setup | HR | 2026-08-02 | 2026-08-06 | 5 | 100%
2 | Day 1 |  | 2026-08-07 | 2026-08-07 | 1 | 0%
2.1 | Orientation & workspace | HR | 2026-08-07 | 2026-08-07 | 1 | 0%
3 | Week 1 |  | 2026-08-08 | 2026-08-12 | 5 | 0%
3.1 | Training & intro meetings | Manager | 2026-08-08 | 2026-08-12 | 5 | 0%
4 | First 90 days |  | 2026-08-13 | 2026-10-30 | 79 | 0%
4.1 | Role ramp & check-ins | Manager | 2026-08-13 | 2026-10-11 | 60 | 0%
5 | 90-day review |  | 2026-10-31 | 2026-10-31 | — | —