## Gantt
EV Charging Installation Schedule
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28
1 | Site assessment & design |  | 2026-08-02 | 2026-08-26 | 25
1.1 | Site walk & capacity check | Engineer | 2026-08-02 | 2026-08-09 | 8
1.2 | Load calculation & layout | Engineer | 2026-08-10 | 2026-08-26 | 17
2 | Utility coordination |  | 2026-08-12 | 2026-10-25 | 75
2.1 | Service application submitted | PM | 2026-08-12 | 2026-08-16 | 5
2.2 | Utility load study & design | Utility | 2026-08-22 | 2026-10-05 | 45
2.3 | Service upgrade scheduled | Utility | 2026-10-06 | 2026-10-25 | 20
3 | ◆ Utility approval |  | 2026-10-26 | 2026-10-26 | [13 empty] | ◆
4 | Permitting |  | 2026-08-30 | 2026-10-03 | 35
4.1 | Electrical & building permits | PM | 2026-08-30 | 2026-09-28 | 30
4.2 | ADA & signage review | PM | 2026-09-16 | 2026-10-03 | 18
5 | Procurement |  | 2026-09-06 | 2026-10-30 | 55
5.1 | Chargers & switchgear ordered | Procurement | 2026-09-06 | 2026-10-25 | 50
6 | Civil & electrical works |  | 2026-10-29 | 2026-12-02 | 35
6.1 | Trenching & conduit | Civil | 2026-10-29 | 2026-11-09 | 12
6.2 | Concrete pads & bollards | Civil | 2026-11-08 | 2026-11-15 | 8
6.3 | Panel work & conductor pull | Electrical | 2026-11-14 | 2026-11-25 | 12
6.4 | Charger mounting | Electrical | 2026-11-24 | 2026-12-02 | 9
7 | Commissioning & activation |  | 2026-12-03 | 2026-12-24 | 22
7.1 | Energization & inspection | Utility | 2026-12-03 | 2026-12-10 | 8
7.2 | Network & payment activation | Ops | 2026-12-11 | 2026-12-19 | 9
8 | ◆ Stations live |  | 2026-12-25 | 2026-12-25 | [21 empty] | ◆