## Slide 1
Grant Proposal Timeline
Free Gantt chart template · gantts.app

## Slide 2
Grant Proposal Timeline
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
Jul 5
Jul 19
Aug 2
Aug 16
Aug 30
Sep 13
Sep 27
Oct 11
Oct 25
Nov 8
Nov 22
Dec 6
Dec 20
Jan 3
Jan 17
Jan 31
Feb 14
Feb 28
Mar 13
Mar 27
Apr 10
Apr 24
May 8
May 22
Jun 5
Jun 19
Jul 3
Jul 17
Jul 31
Aug 14
Aug 28
Sep 11
Sep 25
Oct 9
Oct 23
Nov 6
Nov 20
Dec 4
Dec 18
Jan 1
Jan 15
Jan 29
Feb 12
Feb 26
Mar 12
Mar 26
Apr 9
Apr 23
May 7
May 21
Jun 4
Jun 18
Jul 2
Jul 16
WP1 — Management & coordination
Kick-off & governance
Ongoing coordination
WP2 — Preparation & setup
Ethics & regulatory approval
Recruitment & infrastructure
◆ Setup complete
WP3 — Core work package
Objective 1 activity
Objective 2 activity
◆ Interim results
WP4 — Analysis & validation
Data analysis
Validation & replication
WP5 — Dissemination & impact
Publications
Conferences & stakeholder engagement
Reporting
◆ Year 1 report
◆ Year 2 report
◆ Final report
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | WP1 — Management & coordination |  | 2026-08-02 | 2029-07-16 | 1080 | 20%
1.1 | Kick-off & governance | PI | 2026-08-02 | 2026-09-30 | 60 | 100%
1.2 | Ongoing coordination | PM | 2026-10-01 | 2029-07-16 | 1020 | 15%
2 | WP2 — Preparation & setup |  | 2026-09-01 | 2027-03-29 | 210 | 60%
2.1 | Ethics & regulatory approval | PI | 2026-09-01 | 2026-12-29 | 120 | 80%
2.2 | Recruitment & infrastructure | Team | 2026-12-30 | 2027-03-29 | 90 | 40%
3 | Setup complete |  | 2027-03-30 | 2027-03-30 | — | —
4 | WP3 — Core work package |  | 2027-03-30 | 2028-07-21 | 480 | 0%
4.1 | Objective 1 activity | Team | 2027-03-30 | 2027-11-24 | 240 | 0%
4.2 | Objective 2 activity | Team | 2027-09-26 | 2028-07-21 | 300 | 0%
5 | Interim results |  | 2028-03-24 | 2028-03-24 | — | —
6 | WP4 — Analysis & validation |  | 2028-03-24 | 2029-02-16 | 330 | 0%
6.1 | Data analysis | Analyst | 2028-03-24 | 2028-10-19 | 210 | 0%
6.2 | Validation & replication | Team | 2028-09-20 | 2029-02-16 | 150 | 0%
7 | WP5 — Dissemination & impact |  | 2028-05-23 | 2029-07-16 | 420 | 0%
7.1 | Publications | PI | 2028-05-23 | 2029-03-18 | 300 | 0%
7.2 | Conferences & stakeholder engagement | Team | 2028-09-20 | 2029-07-16 | 300 | 0%
8 | Reporting |  | 2027-07-28 | 2029-07-16 | 720 | 0%
9 | Year 1 report |  | 2027-08-02 | 2027-08-02 | — | —
10 | Year 2 report |  | 2028-08-01 | 2028-08-01 | — | —
11 | Final report |  | 2029-07-17 | 2029-07-17 | — | —