## Slide 1
Hotel Pre-Opening Critical Path
Free Gantt chart template · gantts.app

## Slide 2
Hotel Pre-Opening Critical Path
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Project set-up
Critical path & budget approved
◆ Opening date locked
Recruitment & HR
Executive committee hired
Department heads hired
Line staff hiring wave
OS&E and FF&E procurement
Specify & order OS&E
Delivery & storeroom set-up
Systems & IT
PMS & POS install
Connectivity & integration test
Sales & distribution
Rates, channels & OTA set-up
◆ Bookings open
Pre-opening sales push
Licensing & inspections
Fire, health & liquor licences
◆ Certificate of occupancy
Training & opening
Departmental training
Soft opening
◆ Hotel open
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | Project set-up |  | 2026-08-02 | 2026-08-21 | 20 | 100%
1.1 | Critical path & budget approved | GM | 2026-08-02 | 2026-08-13 | 12 | 100%
2 | Opening date locked |  | 2026-08-22 | 2026-08-22 | — | —
3 | Recruitment & HR |  | 2026-08-22 | 2026-11-29 | 100 | 40%
3.1 | Executive committee hired | HR | 2026-08-22 | 2026-09-20 | 30 | 100%
3.2 | Department heads hired | HR | 2026-09-21 | 2026-10-25 | 35 | 50%
3.3 | Line staff hiring wave | HR | 2026-10-26 | 2026-11-29 | 35 | 0%
4 | OS&E and FF&E procurement |  | 2026-08-27 | 2026-11-29 | 95 | 35%
4.1 | Specify & order OS&E | Purchasing | 2026-08-27 | 2026-10-10 | 45 | 70%
4.2 | Delivery & storeroom set-up | Purchasing | 2026-10-31 | 2026-11-29 | 30 | 0%
5 | Systems & IT |  | 2026-09-26 | 2026-11-29 | 65 | 20%
5.1 | PMS & POS install | IT | 2026-09-26 | 2026-10-25 | 30 | 30%
5.2 | Connectivity & integration test | IT | 2026-10-31 | 2026-11-29 | 30 | 0%
6 | Sales & distribution |  | 2026-09-01 | 2026-12-09 | 100 | 30%
6.1 | Rates, channels & OTA set-up | Commercial | 2026-09-01 | 2026-10-15 | 45 | 50%
7 | Bookings open |  | 2026-10-16 | 2026-10-16 | — | —
7.1 | Pre-opening sales push | Commercial | 2026-10-16 | 2026-12-09 | 55 | 10%
8 | Licensing & inspections |  | 2026-11-10 | 2026-12-19 | 40 | 0%
8.1 | Fire, health & liquor licences | Engineering | 2026-11-10 | 2026-12-04 | 25 | 0%
9 | Certificate of occupancy |  | 2026-12-20 | 2026-12-20 | — | —
10 | Training & opening |  | 2026-11-30 | 2027-01-13 | 45 | 0%

## Slide 4
10.1 | Departmental training | Dept heads | 2026-11-30 | 2026-12-24 | 25 | 0%
10.2 | Soft opening | GM | 2026-12-30 | 2027-01-10 | 12 | 0%
11 | Hotel open |  | 2027-01-14 | 2027-01-14 | — | —