## Slide 1
Wedding Planning (12 months)
Free Gantt chart template · gantts.app

## Slide 2
Wedding Planning (12 months)
Aug 3
Aug 17
Aug 31
Sep 14
Sep 28
Oct 12
Oct 26
Nov 9
Nov 23
Dec 7
Dec 21
Jan 4
Jan 18
Feb 1
Feb 15
Mar 1
Mar 15
Mar 29
Apr 12
Apr 26
May 10
May 24
Jun 7
Jun 21
12-9 months before
Set date, budget & guest list
Book venue
9-6 months before
Caterer, photographer & attire
Send invitations
3-1 months before
RSVPs, seating & rehearsal
◆ Wedding day
Made free at gantts.app

## Slide 3
Task Schedule
# | Task | Owner | Start | End | Days | %
1 | 12-9 months before |  | 2026-08-02 | 2026-10-30 | 90 | 70%
1.1 | Set date, budget & guest list | Couple | 2026-08-02 | 2026-08-21 | 20 | 100%
1.2 | Book venue | Couple | 2026-08-17 | 2026-09-05 | 20 | 80%
2 | 9-6 months before |  | 2026-10-31 | 2027-01-28 | 90 | 30%
2.1 | Caterer, photographer & attire | Couple | 2026-10-31 | 2026-12-29 | 60 | 30%
2.2 | Send invitations | Couple | 2026-12-30 | 2027-01-08 | 10 | 0%
3 | 3-1 months before |  | 2027-03-30 | 2027-05-28 | 60 | 0%
3.1 | RSVPs, seating & rehearsal | Couple | 2027-03-30 | 2027-05-18 | 50 | 0%
4 | Wedding day |  | 2027-06-28 | 2027-06-28 | — | —