## Gantt
Wind Farm Construction Schedule
Made free at gantts.app — edit online and export to Excel, PDF, PNG or PowerPoint
# | Task | Owner | Start | End | Days | Aug 3 | Aug 10 | Aug 17 | Aug 24 | Aug 31 | Sep 7 | Sep 14 | Sep 21 | Sep 28 | Oct 5 | Oct 12 | Oct 19 | Oct 26 | Nov 2 | Nov 9 | Nov 16 | Nov 23 | Nov 30 | Dec 7 | Dec 14 | Dec 21 | Dec 28 | Jan 4 | Jan 11 | Jan 18 | Jan 25 | Feb 1 | Feb 8 | Feb 15 | Feb 22 | Mar 1 | Mar 8 | Mar 15 | Mar 22 | Mar 29 | Apr 5 | Apr 12 | Apr 19 | Apr 26 | May 3 | May 10 | May 17 | May 24 | May 31 | Jun 7 | Jun 14 | Jun 21 | Jun 28 | Jul 5 | Jul 12 | Jul 19 | Jul 26 | Aug 2 | Aug 9 | Aug 16 | Aug 23 | Aug 30 | Sep 6 | Sep 13 | Sep 20 | Sep 27 | Oct 4 | Oct 11 | Oct 18 | Oct 25 | Nov 1 | Nov 8 | Nov 15 | Nov 22 | Nov 29 | Dec 6 | Dec 13 | Dec 20 | Dec 27 | Jan 3 | Jan 10 | Jan 17 | Jan 24 | Jan 31 | Feb 7 | Feb 14 | Feb 21 | Feb 28 | Mar 6 | Mar 13 | Mar 20 | Mar 27 | Apr 3 | Apr 10 | Apr 17 | Apr 24 | May 1 | May 8 | May 15 | May 22 | May 29 | Jun 5 | Jun 12 | Jun 19 | Jun 26 | Jul 3 | Jul 10 | Jul 17 | Jul 24 | Jul 31 | Aug 7 | Aug 14 | Aug 21 | Aug 28 | Sep 4 | Sep 11 | Sep 18 | Sep 25 | Oct 2 | Oct 9 | Oct 16 | Oct 23 | Oct 30 | Nov 6 | Nov 13 | Nov 20 | Nov 27 | Dec 4 | Dec 11 | Dec 18 | Dec 25
1 | Site assessment & resource |  | 2026-08-02 | 2027-09-05 | 400
1.1 | Site selection & land agreements | Development | 2026-08-02 | 2026-10-30 | 90
1.2 | Met mast / LiDAR install | Development | 2026-10-21 | 2026-11-19 | 30
1.3 | Wind resource measurement | Analyst | 2026-11-20 | 2027-09-05 | 290
2 | ◆ Resource confirmed |  | 2027-09-06 | 2027-09-06 | [58 empty] | ◆
3 | Environmental & permitting |  | 2026-12-30 | 2027-11-14 | 320
3.1 | Environmental impact assessment | Consultant | 2026-12-30 | 2027-06-27 | 180
3.2 | Noise & avian surveys | Consultant | 2027-02-18 | 2027-07-17 | 150
4 | ◆ Planning consent |  | 2027-11-15 | 2027-11-15 | [68 empty] | ◆
5 | Grid connection |  | 2027-01-29 | 2028-02-12 | 380
5.1 | Connection application & study | Development | 2027-01-29 | 2027-09-05 | 220
5.2 | Connection agreement & substation design | Engineering | 2027-09-06 | 2028-02-12 | 160
6 | Procurement |  | 2027-11-15 | 2028-06-01 | 200
6.1 | Turbine supply agreement | Procurement | 2027-11-15 | 2028-02-12 | 90
6.2 | Balance of plant & cable orders | Procurement | 2028-01-04 | 2028-06-01 | 150
7 | Civil works |  | 2028-03-24 | 2028-08-20 | 150
7.1 | Access roads & crane pads | Civil | 2028-03-24 | 2028-05-22 | 60
7.2 | Foundations & cure | Civil | 2028-05-03 | 2028-07-31 | 90
7.3 | Cable trenching | Electrical | 2028-05-23 | 2028-07-31 | 70
8 | Erection & commissioning |  | 2028-08-11 | 2028-12-18 | 130
8.1 | Crane mobilization | Erection | 2028-08-11 | 2028-08-30 | 20
8.2 | Tower, nacelle & blade lifts | Erection | 2028-08-29 | 2028-11-01 | 65
8.3 | Electrical termination & testing | Commissioning | 2028-10-25 | 2028-12-03 | 40
9 | ◆ First power |  | 2028-12-19 | 2028-12-19 | [125 empty] | ◆